{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["甘特图","模块明细"],"not_rendered":{"charts":1,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"甘特图","index":0,"n_rows":12,"n_cols":7,"rows_kept":12,"cut":false,"hidden":false,"merged":[[0,1,0,6]]}
["模块","项目甘特图表"]
[null,"/","开始时间","结束时间","负责人","项目持续时间（天）","备注"]
["运营基础","/","2023-05-01","2023-06-01",null,{"$f":"D3-C3","v":31}]
["仓库基础","/","2023-05-01","2023-06-01",null,31]
["工厂数据对接","/","2023-05-17","2023-06-01",null,15]
["预约配送","/","2023-06-01","2023-06-30",null,29]
["仓库管理","/","2023-07-01","2023-07-31",null,30]
["干线运输","/","2023-08-01","2023-08-31",null,30]
["异常售后","/","2023-08-01","2023-08-31",null,30]
["财务结算","/","2023-09-01","2023-10-10",null,39]
["数据报表","/","2023-10-10","2023-11-10",null,31]
["数据大屏","/","2023-10-10","2023-11-10",null,31]

{"sheet":"模块明细","index":1,"n_rows":72,"n_cols":6,"rows_kept":72,"cut":false,"hidden":false,"merged":[[0,1,0,5],[2,0,8,0],[9,0,15,0],[16,0,22,0],[23,0,29,0],[30,0,36,0],[37,0,43,0],[44,0,50,0],[51,0,57,0],[58,0,64,0],[65,0,71,0]]}
["模块","项目甘特图表"]
[null,"任 务","开始时间","结束时间","负责人","项目持续时间（天）"]
["运营基础","需求采集"]
[null,"制作原型"]
[null,"原型审核"]
[null,"迭代开发"]
[null,"系统测试"]
[null,"系统试运行"]
[null,"系统上线"]
["仓库基础","需求采集"]
[null,"制作原型"]
[null,"原型审核"]
[null,"迭代开发"]
[null,"系统测试"]
[null,"系统试运行"]
[null,"系统上线"]
["工厂数据对接","需求采集"]
[null,"制作原型"]
[null,"原型审核"]
[null,"迭代开发"]
[null,"系统测试"]
[null,"系统试运行"]
[null,"系统上线"]
["预约配送","需求采集","2023-06-01","2023-06-06","冯天丽",{"$f":"D24-C24","v":5}]
[null,"制作原型","2023-06-01","2023-06-08","王超、廖杨",7]
[null,"原型审核","2023-06-01","2023-06-08","张松、冯天丽",7]
[null,"迭代开发","2023-06-06","2023-06-30",null,24]
[null,"系统测试","2023-06-30","2023-07-03",null,3]
[null,"系统试运行","2023-07-03","2023-07-14",null,11]
[null,"系统上线","2023-07-15","2023-07-16",null,1]
["仓库管理","需求采集","2023-06-16","2023-06-21","张松、冯天丽",5]
[null,"制作原型","2023-06-21","2023-06-25","王超、廖杨",4]
[null,"原型审核","2023-06-25","2023-06-30","张松、冯天丽",5]
[null,"迭代开发","2023-07-07","2023-07-31",null,24]
[null,"系统测试","2023-08-01","2023-08-04",null,3]
[null,"系统试运行","2023-08-04","2023-08-15",null,11]
[null,"系统上线","2023-08-15","2023-08-16",null,1]
["干线运输","需求采集","2023-08-01","2023-08-05",null,4]
[null,"制作原型","2023-07-21","2023-07-26","王超、廖杨",5]
[null,"原型审核","2023-07-26","2023-07-31",null,5]
[null,"迭代开发","2023-08-05","2023-08-20",null,15]
[null,"系统测试","2023-08-21","2023-08-25",null,4]
[null,"系统试运行","2023-08-25","2023-08-30",null,5]
[null,"系统上线",null,null,null,0]
["异常售后","需求采集",null,null,null,0]
[null,"制作原型",null,null,null,15]
[null,"原型审核",null,null,null,5]
[null,"迭代开发",null,null,null,30]
[null,"系统测试",null,null,null,30]
[null,"系统试运行",null,null,null,30]
[null,"系统上线",null,null,null,5]
["财务结算","需求采集",null,null,null,{"$f":"D52-C52","v":0}]
[null,"制作原型",null,null,null,15]
[null,"原型审核",null,null,null,5]
[null,"迭代开发",null,null,null,30]
[null,"系统测试",null,null,null,30]
[null,"系统试运行",null,null,null,30]
[null,"系统上线",null,null,null,5]
["数据报表","需求采集",null,null,null,{"$f":"D59-C59","v":0}]
[null,"制作原型",null,null,null,15]
[null,"原型审核",null,null,null,5]
[null,"迭代开发",null,null,null,30]
[null,"系统测试",null,null,null,30]
[null,"系统试运行",null,null,null,30]
[null,"系统上线",null,null,null,5]
["数据大屏","需求采集",null,null,null,{"$f":"D66-C66","v":0}]
[null,"制作原型",null,null,null,15]
[null,"原型审核",null,null,null,5]
[null,"迭代开发",null,null,null,30]
[null,"系统测试",null,null,null,30]
[null,"系统试运行",null,null,null,30]
[null,"系统上线",null,null,null,5]